## Overview
AI Customer Assistant - Delivery Plan
Hashthink Technologies - Senior AI Engineer assessment. Review: Mon/Tue Oct 12-13, noon PST.
Progress
Total PRs | 15
PRs done | 8
PRs in progress / review | 0
PRs blocked | 0
Total estimated hours | 29.5
Hours done | 14
Progress (hours-weighted) | 47.46%
User stories mapped | 50
Must-have stories done | 27
Must-have stories total | 39
Capacity vs plan (edit yellow cells)
Day | Available hours | Planned hours | Buffer | PRs planned
Day 1 - Sun Oct 11 | 8 | 8.5 | -0.5 | 6
Day 2 - Mon Oct 12 | 12 | 11.5 | 0.5 | 4
Day 3 - Tue Oct 13 (AM) | 5 | 8 | -3 | 4
Stretch | 0 | 1.5 | -1.5 | 1
Total | 25 | 29.5 | -4.5 | 15
Red buffer = over capacity: move Could-scope out of that day's PRs or shift a Should PR to Stretch.
Hours by phase
Phase | Hours | PRs | Done
Foundation | 2.5 | 3 | 3
RAG | 3.5 | 2 | 2
Agent | 5 | 2 | 2
Customer UI | 3 | 1 | 1
Voice | 4 | 1 | 0
Admin | 8 | 4 | 0
Hardening | 1.5 | 1 | 0
Delivery | 2 | 1 | 0
Legend & workflow
Yellow fill | Cells you edit (Status, Notes, available hours).
Blue text | Hardcoded input / estimate (hours).
Green text | Live lookup from another sheet.
Status values | Not started -> In progress -> In review -> Done (or Blocked).
PR workflow | Branch from main using the Branch column; one PR per row; merge in Depends-on order.
PR description | List the User stories + paste the Definition of done as the test checklist.
Source docs | docs/user-stories.md, docs/ui-design-brief.md
Note on B18: Assumption: hours you can realistically work each day. Edit to match your schedule.

## PR Plan
AI Customer Assistant - PR Plan
One row = one pull request. Edit Status / Notes (yellow columns). Story counts are calculated from the Story Coverage sheet.
PR # | Branch | Title | Phase | Priority | User stories | Scope / tasks | Definition of done (test plan) | Decisions to defend on the call | Depends on | Est. hours | Planned day | Status | # Stories (primary) | Notes
PR-01 | chore/01-project-scaffold | Project scaffold & tooling | Foundation | Must | US-12.1 (env/secrets setup) | - Next.js (App Router) + TypeScript strict + Tailwind - Folder layout: app/, lib/agent, lib/rag, lib/db, scripts/, supabase/, docs/ - .env.example (OpenAI key, Supabase URL/service key, model names) - Typed env loader (zod) that fails fast on missing vars - Supabase CLI as devDependency, npm scripts (db:start, db:reset, ingest) - README skeleton | - npm run dev / build / lint pass - App fails at boot with a clear message if an env var is missing - No secret is referenced from client code | Why Next.js route handlers instead of a separate API; why env validated at boot; why model names are configurable | - | 0.5 | Day 1 - Sun Oct 11 | Done | 0 | Merged: PR #1
PR-02 | feat/02-database-schema | Database schema, constraints & RLS | Foundation | Must | US-12.2, US-4.3, US-5.3, US-7.2 (DB side) | - Migration: businesses, documents, chunks (vector 1536 + HNSW), conversations, messages, tool_calls, leads, consultation_requests - Constraints: email lowercase, email OR phone, unique lead per business, unique consultation (lead, service, time), content_hash dedupe - match_chunks(business_id, embedding, k, min_similarity) SQL function - RLS enabled on all tables, no public policies - Seed: demo business row - Typed Supabase server client (service role, server-only) | - supabase db reset applies cleanly - Inserting duplicate lead / consultation is rejected by Postgres - anon key cannot select from any table | Invariants in the schema not the app; why tool_calls separate from messages; HNSW vs IVFFlat; denormalised business_id on chunks; one conversation per session | PR-01 | 1.5 | Day 1 - Sun Oct 11 | Done | 1 | Merged: PR #3. Design doc reviewed first (PR #2). Three review rounds; verified as service_role.
PR-03 | feat/03-sample-clinic-docs | Sample business knowledge (Lakeside Dental) | Foundation | Must | Supports E3 demo | - 5-6 docs: services.md, pricing.md, hours-location.md, insurance-payment.md, faq.md, policies.pdf (text PDF) - Realistic headings so heading-aware chunking can be shown - Include facts used in the demo script (whitening price, hours, insurance) - Deliberately omit some topics to demo 'I don't know' | - Docs reviewed for internal consistency (no conflicting prices) - Each demo question has exactly one clear answer source | Why test data is designed around the demo questions; why include a PDF | PR-02 | 0.5 | Day 1 - Sun Oct 11 | Done | 0 | Merged: PR #4. Data lives in data/sample-clinic/ (not docs/). PDF export needed the Writer filter.
PR-04 | feat/04-rag-ingestion | RAG ingestion pipeline | RAG | Must | US-7.1 (backend), US-7.2, US-11.5 | - Text extraction: .txt, .md, text PDF (pdf-parse); detect scanned PDF (no text) -> clear error - Heading-aware chunker: split by headings/paragraphs, ~400-500 tokens, ~60 token overlap - Prefix chunk with 'Doc title > Section' before embedding - Batch embeddings (text-embedding-3-small) - sha256 content hash dedupe - Status lifecycle processing -> ready ¦ failed; no partial chunks on failure - CLI: npm run ingest -- ./docs/sample-clinic | - Ingesting sample docs creates chunks with embeddings - Re-ingesting same file is a no-op - Scanned/empty PDF -> status failed with reason - Unit tests for the chunker (headings, overlap, long sections) | Chunk size & overlap reasoning; heading prefix (contextual chunks); why tokens not words; embedding model choice & cost; idempotent ingestion | PR-02 | 2 | Day 1 - Sun Oct 11 | Done | 2 | Merged: PR #5. Verified with real embeddings (60 chunks). Finding for PR-05: a single similarity threshold can't separate found/not-found.
PR-05 | feat/05-retrieval | Retrieval service + search_knowledge | RAG | Must | US-3.1, US-3.2 (data), US-3.3 (threshold) | - retrieve(businessId, query): embed query -> match_chunks top 6 - Hybrid search (vector + full-text, RRF) and a found rule -> {found:false} when nothing relevant - Return sources: documentId, title, heading, excerpt, similarity - Eval script: ~10 demo questions + expected source doc, prints hit/miss | - Eval script: all answerable questions retrieve the right doc in top 3 - Out-of-scope questions return found:false - Threshold value documented with the reasoning | Why hybrid instead of a similarity threshold (measured: 0.27 correct vs 0.42 wrong); RRF; what a 'topic keyword' is and why frame verbs are excluded; sources come from retrieval not the LLM; reranker as the production next step | PR-04 | 1.5 | Day 1 - Sun Oct 11 | Done | 3 | Merged: PR #6. Hybrid search (D-13) replaced the planned threshold after measurement. Eval 15/15 found, 6/6 gaps; pgTAP tests added.
PR-06 | feat/06-agent-tools | Agent core: prompt + tools + validation | Agent | Must | US-3.3, US-3.4, US-4.1, US-4.2, US-4.3, US-5.1, US-5.2, US-5.3, US-11.1, US-11.2, US-12.4, US-12.5 | - System prompt builder: business profile, current date/time + timezone, grounding rules, safety rules (no diagnosis, emergencies), lead facts block - Tool registry shared by text & voice: search_knowledge, save_lead, create_consultation_request - Zod schemas (email, phone normalisation, future date <= 6 months) - Executors return {ok, data ¦ error}; never throw to the model - Upsert lead, link conversation.lead_id - Every call logged to tool_calls (args, result, ok, duration) | - Unit tests: invalid email/phone/date -> ok:false with readable error - Duplicate lead/consultation -> returns existing, no new row - DB error -> ok:false 'temporarily unavailable' - Tool call rows written for success and failure | Why these 3 tools; errors as tool results so the model can recover; validation at tool boundary; idempotency; prompt-injection limits via tool scope | PR-05 | 2.5 | Day 1 - Sun Oct 11 | Done | 11 | Merged: PR #7. Tools as atomic SQL functions; outcome_unknown for timed-out writes; prompt ordered for caching; R1 tested.
PR-07 | feat/07-chat-api-memory | Chat API: agent loop, streaming & memory | Agent | Must | US-1.2 (server), US-6.1, US-6.2, US-6.3, US-11.3, US-11.4, US-12.3 | - POST /api/chat {sessionId, message}: validate (non-empty, <= 2000 chars) - Get-or-create conversation by (business, session) - Load last 20 messages + lead facts server-side - Hand-written loop: model -> tool calls -> results -> repeat (max 5 rounds) - Stream to client (SSE): text deltas, tool status events, sources, action cards - Persist user + assistant messages with sources - Timeouts + friendly fallback on OpenAI failure - GET /api/conversations/:session for history | - Follow-up question resolved from history - Returning session loads previous messages - Lead known -> assistant doesn't re-ask - Forced tool loop stops at 5 rounds - OpenAI error -> friendly message, user msg still saved | Hand-written loop vs AI SDK; server is source of truth for history; sliding window size & cost; why tool traffic is not replayed; streaming protocol | PR-06 | 2.5 | Day 2 - Mon Oct 12 | Done | 6 | Merged: PR #8. Three review rounds: retry lease, one turn per conversation, integration tests.
PR-08 | feat/08-chat-ui | Customer chat UI | Customer UI | Must | US-1.1, US-1.2, US-1.3, US-1.4, US-1.5, US-3.2 (UI), US-11.6 | - Anonymous session id in localStorage - Welcome state + suggested questions - Message list: user/assistant bubbles, markdown, streaming caret, thinking + tool status lines - Source chips + excerpt popover / bottom sheet - Action cards: lead saved, consultation requested (Pending), failed - Composer: auto-grow, Enter/Shift+Enter, counter, disabled states - Error states: send failed + retry, AI unavailable, offline - Mobile layout, aria-live region - Chat page at /b/[slug]; business name and description loaded from the server, nothing hardcoded (/ goes to the default business until PR-15) - Retry offered only on the latest failed message; partial streamed text replaced by the error state - Collapse repeated 'details saved' cards | - Demo scenarios 1-5 work end to end in the browser - Works at 360px width - Keyboard-only usable - Retry doesn't duplicate the message | Why citations rendered from structured data; streaming UX; accessibility basics; per-business route from day one, so PR-15 needs no rework | PR-07 | 3 | Day 2 - Mon Oct 12 | Done | 6 | Merged: PR #10. Chat API takes the business slug (/b/[slug]). One review round: bounded business cache, history race, reload mid-answer polling, memoized streaming, repeated save_lead deduped in the loop.
PR-09 | feat/09-realtime-voice | Realtime voice (OpenAI Realtime + WebRTC) | Voice | Must | US-2.1, US-2.2, US-2.3, US-2.4, US-2.5, US-2.6, US-6.4, US-12.1 | - POST /api/voice/session: the server opens the Realtime call for the browser's SDP offer, with the same instructions + tool definitions + recent history (no key or token in the browser) - Browser WebRTC: mic track, remote audio, data channel - Server VAD (natural turn-taking, barge-in) - Tool relay: data channel function_call -> POST /api/voice/tool -> function_call_output - Persist user/assistant transcripts (channel=voice) - Voice panel UI: states, orb, mute, end, permission & error handling | - Ask a question by voice -> spoken answer with sources in thread - Interrupt mid-answer works - Lead + consultation created by voice (same DB rows as text) - End voice -> typed follow-up has voice context - API key never in browser network tab | WebRTC vs WebSocket; ephemeral tokens; one tool layer for both channels; why not Whisper+TTS (latency); voice cost per minute | PR-06, PR-07 | 4 | Day 2 - Mon Oct 12 | Not started | 8
PR-10 | feat/10-admin-knowledge-base | Admin shell + knowledge base | Admin | Must | US-7.1, US-7.2 (UI), US-7.3, US-7.4, US-7.5 | - Admin layout: sidebar nav, 'Demo mode - no login' label - Upload API (multipart, type/size validation, 10MB) reusing ingestion pipeline - Dropzone + upload queue with statuses - Documents table + delete (cascades chunks) - (Could) document detail with sections; test search box | - Upload new doc -> Ready -> answer about it in chat (demo scenario 8) - Unsupported type rejected before upload - Delete -> assistant stops citing it | Synchronous vs background ingestion (and when to move to a queue); admin auth out of scope and how you'd add it | PR-04 | 2 | Day 2 - Mon Oct 12 | Not started | 4
PR-11 | feat/11-admin-leads-consultations | Admin: leads, consultations & overview | Admin | Must | US-8.1, US-8.2, US-8.3 | - Leads table + lead drawer (requests, link to conversation) - Consultations table, status filter (Pending default), status change with optimistic update - Overview KPIs (7-day counts, pending requests) | - Lead/request created in chat appears here - Status change persists; failure reverts with toast - Times shown in business timezone | Pagination/limits on lists; timezone handling (store UTC, display business tz) | PR-06 | 1.5 | Day 3 - Tue Oct 13 (AM) | Not started | 3
PR-12 | feat/12-admin-conversations-settings | Admin: conversation review & AI audit trail | Admin | Should | US-9.1, US-9.2, US-9.3 | - Conversations list + transcript view - Inline tool-call rows (args, result, duration, failed highlighted) - (Could) unanswered questions list from search found:false | - Demo shows tool audit trail for a real conversation | Observability of agent actions; knowledge-gap loop as product value | PR-07 | 1.5 | Stretch | Not started | 3
PR-13 | fix/13-reliability-hardening | Reliability & failure handling pass | Hardening | Must | US-11.1 - US-11.6 (verification), US-12.6 | - Fault injection flag (e.g. SIMULATE_DB_FAILURE) to demo DB outage - Structured logs (conversation id, latency, tool, error) - Basic per-session rate limit - Walk every error state in UI & fix gaps - Prompt-injection & off-topic manual tests | - Demo scenario 9: DB down -> no false confirmation - All error states in the design brief reachable and handled - Checklist of failure tests in README | Failure modes & recovery; why never claim success without ok:true; rate limiting approach | PR-07, PR-08, PR-09 | 1.5 | Day 3 - Tue Oct 13 (AM) | Not started | 1
PR-14 | docs/14-readme-demo | README, architecture & demo video | Delivery | Must | All (deliverables) | - README: setup (Docker, supabase start, env, ingest, dev), architecture diagram, decisions, limitations, cost/latency notes, future work - Demo script from user-stories section 11 - Record 3-5 min video (text, voice, RAG, actions, admin, failure) | - Fresh clone -> running app following README only - Video covers all 9 demo scenarios | Be ready to walk through the architecture diagram and every row of the Decision Log | All | 2 | Day 3 - Tue Oct 13 (AM) | Not started | 0
PR-15 | feat/15-multi-business | Multi-business: home page, add business, per-business guidelines | Admin | Should | US-10.1, US-10.2 | - Home page lists businesses as cards; each opens its chat at /b/[slug] - Admin -> New business: name, slug, description, timezone, assistant guidelines - Admin -> Settings: edit the same fields for the selected business (US-10.1) - businesses.assistant_guidelines column; clinic-specific rules (no diagnosis, 911) move there from the shared prompt; neutral examples in the shared prompt and tool descriptions - Admin pages scoped to the selected business (documents, leads, requests) - Second sample business (data/sample-gym) prepared for the live demo | - Create a business in the admin, upload its docs, open its card -> answers from its documents with sources - Lakeside answers unchanged; no cross-business results (every query filtered by business) - Shared prompt contains no clinic-specific rule (prompt test) - Live demo rehearsed: add 'Acme Fitness' in under 2 minutes | One assistant per business, many businesses as data; why the picker is a local demo device, not a product flow; per-business guidelines vs hardcoded rules; tenant isolation by business_id | PR-08, PR-10 | 3 | Day 3 - Tue Oct 13 (AM) | Not started | 2 | Agreed Oct 11. Core requirements first; this is the first item dropped if time runs short.
TOTAL | [9 empty] | 29.5 |  |  | 50
Estimates assume focused work with an AI pair; adjust freely.

## Story Coverage
User Story Coverage
Every story from docs/user-stories.md mapped to the PR that delivers it. Status is looked up from the PR Plan.
Story ID | Epic | Story | Priority | Primary PR | Also touched in | PR status (live) | PR planned day (live)
US-1.1 | E1 Web chat | Start a conversation without signing up | Must | PR-08 | PR-07 | Done | Day 2 - Mon Oct 12
US-1.2 | E1 Web chat | Send a message and see a streaming reply | Must | PR-08 | PR-07 | Done | Day 2 - Mon Oct 12
US-1.3 | E1 Web chat | Input validation in the composer | Must | PR-08 | PR-07 | Done | Day 2 - Mon Oct 12
US-1.4 | E1 Web chat | Mobile-friendly chat | Must | PR-08 |  | Done | Day 2 - Mon Oct 12
US-1.5 | E1 Web chat | Start a new conversation | Could | PR-08 |  | Done | Day 2 - Mon Oct 12
US-2.1 | E2 Voice | Talk to the assistant | Must | PR-09 |  | Not started | Day 2 - Mon Oct 12
US-2.2 | E2 Voice | Interrupt the assistant | Must | PR-09 |  | Not started | Day 2 - Mon Oct 12
US-2.3 | E2 Voice | Live captions | Must | PR-09 |  | Not started | Day 2 - Mon Oct 12
US-2.4 | E2 Voice | Voice takes the same actions as text | Must | PR-09 | PR-06 | Not started | Day 2 - Mon Oct 12
US-2.5 | E2 Voice | Control and end the voice session | Must | PR-09 |  | Not started | Day 2 - Mon Oct 12
US-2.6 | E2 Voice | Voice unavailable | Must | PR-09 |  | Not started | Day 2 - Mon Oct 12
US-3.1 | E3 RAG | Accurate answers from the business's documents | Must | PR-05 | PR-04 | Done | Day 1 - Sun Oct 11
US-3.2 | E3 RAG | See where an answer came from | Must | PR-05 | PR-08 | Done | Day 1 - Sun Oct 11
US-3.3 | E3 RAG | Honest 'I don't know' | Must | PR-05 | PR-06 | Done | Day 1 - Sun Oct 11
US-3.4 | E3 RAG | Stay on topic and within limits | Must | PR-06 |  | Done | Day 1 - Sun Oct 11
US-4.1 | E4 Leads | Share my contact details in conversation | Must | PR-06 | PR-08 | Done | Day 1 - Sun Oct 11
US-4.2 | E4 Leads | Invalid details are caught | Must | PR-06 |  | Done | Day 1 - Sun Oct 11
US-4.3 | E4 Leads | No duplicate leads | Must | PR-06 | PR-02 | Done | Day 1 - Sun Oct 11
US-5.1 | E5 Consultations | Request a consultation in conversation | Must | PR-06 | PR-08 | Done | Day 1 - Sun Oct 11
US-5.2 | E5 Consultations | Invalid consultation inputs are caught | Must | PR-06 |  | Done | Day 1 - Sun Oct 11
US-5.3 | E5 Consultations | No duplicate requests | Must | PR-06 | PR-02 | Done | Day 1 - Sun Oct 11
US-6.1 | E6 Memory | Remember earlier messages | Must | PR-07 |  | Done | Day 2 - Mon Oct 12
US-6.2 | E6 Memory | Continue where I left off | Must | PR-07 | PR-08 | Done | Day 2 - Mon Oct 12
US-6.3 | E6 Memory | Don't ask for details I already gave | Must | PR-07 | PR-06 | Done | Day 2 - Mon Oct 12
US-6.4 | E6 Memory | Seamless switch between text and voice | Must | PR-09 | PR-07 | Not started | Day 2 - Mon Oct 12
US-7.1 | E7 Knowledge base | Upload business documents | Must | PR-10 | PR-04 | Not started | Day 2 - Mon Oct 12
US-7.2 | E7 Knowledge base | Avoid duplicate documents | Must | PR-04 | PR-10 | Done | Day 1 - Sun Oct 11
US-7.3 | E7 Knowledge base | See and remove documents | Must | PR-10 |  | Not started | Day 2 - Mon Oct 12
US-7.4 | E7 Knowledge base | Preview what the assistant learned | Could | PR-10 |  | Not started | Day 2 - Mon Oct 12
US-7.5 | E7 Knowledge base | Test the assistant against my documents | Could | PR-10 | PR-05 | Not started | Day 2 - Mon Oct 12
US-8.1 | E8 Leads & consultations | View leads | Must | PR-11 |  | Not started | Day 3 - Tue Oct 13 (AM)
US-8.2 | E8 Leads & consultations | View consultation requests | Must | PR-11 |  | Not started | Day 3 - Tue Oct 13 (AM)
US-8.3 | E8 Leads & consultations | Update request status | Should | PR-11 |  | Not started | Day 3 - Tue Oct 13 (AM)
US-9.1 | E9 Conversation review | Read customer conversations | Should | PR-12 |  | Not started | Stretch
US-9.2 | E9 Conversation review | See what the AI did and why | Should | PR-12 | PR-06 | Not started | Stretch
US-9.3 | E9 Conversation review | Spot knowledge gaps | Could | PR-12 |  | Not started | Stretch
US-10.1 | E10 Business profile | Edit business profile | Should | PR-15 | PR-12 | Not started | Day 3 - Tue Oct 13 (AM)
US-11.1 | E11 Reliability | Tool failures don't break the conversation | Must | PR-06 | PR-13 | Done | Day 1 - Sun Oct 11
US-11.2 | E11 Reliability | Invalid tool inputs caught before the DB | Must | PR-06 |  | Done | Day 1 - Sun Oct 11
US-11.3 | E11 Reliability | AI provider failures | Must | PR-07 | PR-13 | Done | Day 2 - Mon Oct 12
US-11.4 | E11 Reliability | No runaway agent loops | Must | PR-07 |  | Done | Day 2 - Mon Oct 12
US-11.5 | E11 Reliability | Document ingestion failures | Must | PR-04 |  | Done | Day 1 - Sun Oct 11
US-11.6 | E11 Reliability | Network loss in the browser | Must | PR-08 | PR-13 | Done | Day 2 - Mon Oct 12
US-12.1 | E12 Security | Secrets never reach the browser | Must | PR-09 | PR-01 | Not started | Day 2 - Mon Oct 12
US-12.2 | E12 Security | Database not publicly accessible | Must | PR-02 |  | Done | Day 1 - Sun Oct 11
US-12.3 | E12 Security | Conversation history can't be tampered with | Must | PR-07 |  | Done | Day 2 - Mon Oct 12
US-12.4 | E12 Security | Prompt-injection resistance | Must | PR-06 | PR-13 | Done | Day 1 - Sun Oct 11
US-12.5 | E12 Security | Data minimisation | Should | PR-06 |  | Done | Day 1 - Sun Oct 11
US-12.6 | E12 Security | Abuse protection (rate limit) | Could | PR-13 |  | Not started | Day 3 - Tue Oct 13 (AM)
US-10.2 | E10 Business profile | Add another business with its own documents | Should | PR-15 | PR-10 | Not started | Day 3 - Tue Oct 13 (AM)

## Decision Log
Architecture Decision Log
Prepare to defend each of these on the review call: what, the alternative, why, and the trade-off.
ID | Area | Decision | Alternative considered | Why | Trade-off / risk | PR
D-01 | Agent loop | Hand-written tool loop with the openai SDK | Vercel AI SDK / LangChain agents | ~100 lines I can explain line by line; full control of max rounds, timeouts, logging | More plumbing for streaming; would adopt AI SDK for streaming in production | PR-07
D-02 | Retrieval | search_knowledge as a tool (agentic RAG) | Always retrieve before every message | Model skips search for small talk, rewrites vague follow-ups, can search twice | +1 model round trip (~300-600 ms) when searching | PR-06
D-03 | Hallucination | Layered: grounding prompt + hybrid retrieval found-rule + sources only from retrieval + no facts in prompt | Prompt-only 'don't make things up' | Each layer catches what the previous misses; citations cannot be invented | Originally planned a similarity threshold as layer 2; measurement showed it cannot work (see D-13). The retrieval gate filters noise; the prompt is the main defence | PR-05
D-04 | Chunking | Heading-aware, ~400-500 tokens, ~60 overlap, title > section prefix | Fixed-size character splits | Keeps FAQ answers / price tables whole; prefix improves retrieval of short chunks | Uneven chunk sizes; more code than a naive splitter | PR-04
D-05 | Vector store | Supabase pgvector + HNSW | Pinecone / dedicated vector DB | Required stack; one database for vectors + relational data + transactions | At very large scale a dedicated store may be faster | PR-02
D-06 | Memory | Server-side sliding window (20 msgs) + structured lead facts | Client sends history / vector memory of chats | Tamper-proof; cheap; facts that matter (who the customer is) are exact | Very long conversations lose early detail (summary is next step) | PR-07
D-07 | Voice | OpenAI Realtime over WebRTC; the server opens the call (relays the SDP offer), so no key or token reaches the browser | Whisper STT + LLM + TTS pipeline | Lowest latency, natural turn-taking and barge-in; key never in browser | Higher cost per minute; tool calls and transcripts are relayed by the browser (a server-side connection to the call is the production next step) | PR-09
D-08 | Tools | One tool layer shared by text and voice | Separate implementations per channel | Identical validation and DB behaviour; no drift between channels | Voice tool calls need a relay endpoint | PR-06
D-09 | Errors | Tool errors returned to the model as {ok:false,error} | Throw / 500 the request | Model can recover (ask user to fix email, apologise for outage); never fakes success | Need prompt rule + tests to ensure model respects ok:false | PR-06
D-10 | Data integrity | Invariants as DB constraints (unique lead, unique request, email check) | Checks only in application code | Safe against retries and races; idempotent tool calls | Constraint errors must be mapped to friendly results | PR-02
D-11 | Security | RLS on, no policies; all access via server with service role | Supabase client in browser with RLS policies | Simplest secure model for anonymous users; no data exposure via anon key | All reads go through API routes | PR-02
D-12 | Local dev | Supabase local via Docker + migrations in repo | Hosted project only | Reproducible setup for reviewers; same migrations deploy to hosted with db push | Requires Docker; no public demo URL | PR-01
D-13 | Retrieval gate | Hybrid search (vector + Postgres full-text, reciprocal rank fusion) with a topic-keyword found rule | Plain similarity threshold (the original plan); reranker / LLM relevance grader | Measured on real embeddings: the weakest correct answer scored 0.27 while the strongest wrong match for an out-of-scope question scored 0.42, so no threshold separates them. A topic keyword either occurs in the knowledge base or it doesn't. Hybrid+RRF is the industry-standard pattern; eval: 14/14 found, 5/5 gaps rejected | Second index and ~ms per search; the found rule's frame-verb exclusion is a heuristic. Production upgrade: a reranker or LLM relevance grader (calibrated 'does this chunk answer the question?' scores) at ~200-400 ms per search | PR-05
D-14 | Scope | One assistant per business; many businesses as data. A home-page picker and 'add business' admin exist for the local demo | Business directory / SaaS multi-tenancy (tenant routing, sign-up, per-tenant auth) | The task asks for an assistant for a business. Learning the business from documents makes the code generic for free; adding a second business live in the meeting proves it without building a platform | A picker isn't a real customer flow (customers arrive from the business's own website); tenant-scoped admin auth would be needed before any deployment | PR-15